## Sheet1
ID | AS A | I WANT TO | SO THAT | PRIORITY | SPRINT | STATUS | TEAM MEMBER
1 | User | view public playlists | I am able to turn them into courses | High | 1 | Done | Mariana
2 | User | be able to register |  | High | 1 | To do | Cary
3 | User | be able to login |  | High | 1 | In progress | Mariana and Cary
4 | User | see the duration of playlist | I can choose better playlists | Low | 1 | Done | Mariana
5 | User | logout |  | High | 1 | Done | Mariana
6 | User | follow other users | i am able to see their courses | High | 2 | To do
7 | User | view the playlists of the people I follow |  | High | 2 | To do
8 | User | view my playlists | I am able to turn them into courses | High | 2 | To do
9 | User | turn any playlist into a course |  | High | 2 | To do
10 | User | unfollower a user |  | Medium | 3 | To do
11 | User | view all my courses |  | High | 3 | To do
12 | User | search playlist by topic |  | Medium | 3 | To do
13 | User | view the profile of another user |  | Medium | 3 | To do